## POAP
Tower | Tower Rag | Task Name | Resource Names | Milestone at Risk | Milestone Level | Milestone Level Name | Milestone Icon | Task Nomenclature | Milestone Status | Milestone Rag | Start | Status | Finish | Duration | % Complete | Notes | Today Date | Task No | 30 days Ago | Milestone Due
Tom | #C0C0C0 | Tom Including Common Services | Mark Curry | No | 2 | Level 2 | ▲ | Tom Including Common Services - 23/09/2022 - ▲ | Complete | #1c4e80 | 2022-09-23 | Complete | 2022-09-23 | 0 | 100% | what is the deliverable? | 2022-11-22 | 1 | 2022-10-23 | Other Completed
Tom | #C0C0C0 | Tom (Tbc) | Mark Curry | No | 2 | Level 2 | ▲ | Tom (Tbc) - 30/12/2022 - ▲ | In Progress | #6ab187 | 2022-12-30 | Future Task | 2022-12-30 | 0 | 0% | what is the deliverable? | 2022-11-22 | 2 | 2022-10-23 | due in 60 days
Hosting & Network | #69D1C5 | Wi Fi Vendor Selected | Carl Smith | No | 2 | Level 2 | ▲ | Wi Fi Vendor Selected - 29/04/2022 - ▲ | Complete | #1c4e80 | 2022-04-29 | Complete | 2022-04-29 | 0 | 100% |  | 2022-11-22 | 3 | 2022-10-23 | Other Completed
Hosting & Network | #69D1C5 | Supplier Rfi Reviewed And Scored (Down Selection) | Carl Smith | No | 3 | Level 3 | ◆ | Supplier Rfi Reviewed And Scored (Down Selection) - 13/05/2022 - ◆ | Complete | #1c4e80 | 2022-05-13 | Complete | 2022-05-13 | 0 | 100% |  | 2022-11-22 | 4 | 2022-10-23 | Other Completed
Hosting & Network | #69D1C5 | Wifi Hw Contract | Carl Smith | No | 2 | Level 2 | ▲ | Wifi Hw Contract - 12/08/2022 - ▲ | Complete | #1c4e80 | 2022-08-12 | Complete | 2022-08-12 | 0 | 100% |  | 2022-11-22 | 5 | 2022-10-23 | Other Completed
Hosting & Network | #69D1C5 | Rfi Responses From Vendors | Carl Smith | No | 3 | Level 3 | ◆ | Rfi Responses From Vendors - 26/08/2022 - ◆ | Complete | #1c4e80 | 2022-08-26 | Complete | 2022-08-26 | 0 | 100% |  | 2022-11-22 | 6 | 2022-10-23 | Other Completed
Hosting & Network | #69D1C5 | Wifi Ms Contracted | Carl Smith | No | 2 | Level 2 | ▲ | Wifi Ms Contracted - 16/09/2022 - ▲ | Complete | #1c4e80 | 2022-09-16 | Complete | 2022-09-16 | 0 | 100% |  | 2022-11-22 | 7 | 2022-10-23 | Other Completed
Hosting & Network | #69D1C5 | Cto Application Roadmap Completed | Carl Smith | No | 2 | Level 2 | ▲ | Cto Application Roadmap Completed - 30/06/2022 - ▲ | Complete | #1c4e80 | 2022-06-30 | Complete | 2022-06-30 | 0 | 100% |  | 2022-11-22 | 8 | 2022-10-23 | Other Completed
Hosting & Network | #69D1C5 | Communication Strategy For Capgemini | Carl Smith | No | 2 | Level 2 | ▲ | Communication Strategy For Capgemini - 01/07/2022 - ▲ | Complete | #1c4e80 | 2022-07-01 | Complete | 2022-07-01 | 0 | 100% |  | 2022-11-22 | 9 | 2022-10-23 | Other Completed
Hosting & Network | #69D1C5 | Capgemini Engaged In Planning | Carl Smith | No | 3 | Level 3 | ◆ | Capgemini Engaged In Planning - 30/09/2022 - ◆ | Complete | #1c4e80 | 2022-09-30 | Complete | 2022-09-30 | 0 | 100% |  | 2022-11-22 | 10 | 2022-10-23 | Other Completed
Hosting & Network | #69D1C5 | Tom L1 Complete | Carl Smith | No | 2 | Level 2 | ▲ | Tom L1 Complete - 30/09/2022 - ▲ | Complete | #1c4e80 | 2022-09-30 | Complete | 2022-09-30 | 0 | 100% |  | 2022-11-22 | 11 | 2022-10-23 | Other Completed
Hosting & Network | #69D1C5 | Migration Partner Cmds Data | Carl Smith | No | 3 | Level 3 | ◆ | Migration Partner Cmds Data - 03/10/2022 - ◆ | Complete | #1c4e80 | 2022-10-03 | Complete | 2022-10-03 | 0 | 100% |  | 2022-11-22 | 12 | 2022-10-23 | Other Completed
Hosting & Network | #69D1C5 | Ph1 Cloud Landing Zone Design | Carl Smith | No | 3 | Level 3 | ◆ | Ph1 Cloud Landing Zone Design - 04/11/2022 - ◆ | Overdue | #EA0707 | 2022-11-04 | Future Task | 2022-11-04 | 0 | 0% |  | 2022-11-22 | 13 | 2022-10-23 | Overdue
Hosting & Network | #69D1C5 | Non Exotics App Assessed | Carl Smith | No | 3 | Level 3 | ◆ | Non Exotics App Assessed - 18/11/2022 - ◆ | Overdue | #EA0707 | 2022-11-18 | Future Task | 2022-11-18 | 0 | 0% |  | 2022-11-22 | 14 | 2022-10-23 | Overdue
Hosting & Network | #69D1C5 | Start Wifi Implementation (As) | Carl Smith | No | 3 | Level 3 | ◆ | Start Wifi Implementation (As) - 30/11/2022 - ◆ | In Progress | #6ab187 | 2022-11-30 | Future Task | 2022-11-30 | 0 | 0% |  | 2022-11-22 | 15 | 2022-10-23 | due in 30 days
Hosting & Network | #69D1C5 | Aws To Azure Connectivity (Temp) | Carl Smith | No | 3 | Level 3 | ◆ | Aws To Azure Connectivity (Temp) - 30/11/2022 - ◆ | In Progress | #6ab187 | 2022-11-30 | Future Task | 2022-11-30 | 0 | 0% |  | 2022-11-22 | 16 | 2022-10-23 | due in 30 days
Hosting & Network | #69D1C5 | Ph1 Landing Zone Ready | Carl Smith | No | 2 | Level 2 | ▲ | Ph1 Landing Zone Ready - 09/12/2022 - ▲ | In Progress | #6ab187 | 2022-12-09 | Future Task | 2022-12-09 | 0 | 0% |  | 2022-11-22 | 17 | 2022-10-23 | due in 30 days
Hosting & Network | #69D1C5 | E2E Hosting And Network Design | Carl Smith | No | 2 | Level 2 | ▲ | E2E Hosting And Network Design - 23/12/2022 - ▲ | In Progress | #6ab187 | 2022-12-23 | Future Task | 2022-12-23 | 0 | 0% |  | 2022-11-22 | 18 | 2022-10-23 | due in 60 days
Hosting & Network | #69D1C5 | Tom Interim | Carl Smith | No | 2 | Level 2 | ▲ | Tom Interim - 30/12/2022 - ▲ | In Progress | #6ab187 | 2022-12-30 | Future Task | 2022-12-30 | 0 | 0% |  | 2022-11-22 | 19 | 2022-10-23 | due in 60 days
Hosting & Network | #69D1C5 | Co Lo Requirements Defined | Carl Smith | No | 3 | Level 3 | ◆ | Co Lo Requirements Defined - 06/01/2023 - ◆ | In Progress | #6ab187 | 2023-01-06 | Future Task | 2023-01-06 | 0 | 0% |  | 2022-11-22 | 20 | 2022-10-23 | due in 60 days
Hosting & Network | #69D1C5 | Migration Partner Contract In Place | Carl Smith | No | 3 | Level 3 | ◆ | Migration Partner Contract In Place - 06/01/2023 - ◆ | In Progress | #6ab187 | 2023-01-06 | Future Task | 2023-01-06 | 0 | 0% |  | 2022-11-22 | 21 | 2022-10-23 | due in 60 days
Hosting & Network | #69D1C5 | Ph2 Cloud Landing Zone Design | Carl Smith | No | 3 | Level 3 | ◆ | Ph2 Cloud Landing Zone Design - 13/01/2023 - ◆ | In Progress | #6ab187 | 2023-01-13 | Future Task | 2023-01-13 | 0 | 0% |  | 2022-11-22 | 22 | 2022-10-23 | due in 60 days
Hosting & Network | #69D1C5 | Non Capgemini Hosted App Assessment | Carl Smith | No | 3 | Level 3 | ◆ | Non Capgemini Hosted App Assessment - 20/01/2023 - ◆ | In Progress | #6ab187 | 2023-01-20 | Future Task | 2023-01-20 | 0 | 0% |  | 2022-11-22 | 23 | 2022-10-23 | due in 60 days
Hosting & Network | #69D1C5 | Co Lo Rfp Issued | Carl Smith | No | 3 | Level 3 | ◆ | Co Lo Rfp Issued - 20/01/2023 - ◆ | In Progress | #6ab187 | 2023-01-20 | Future Task | 2023-01-20 | 0 | 0% |  | 2022-11-22 | 24 | 2022-10-23 | due in 60 days
Hosting & Network | #69D1C5 | Network Rfp Issued | Carl Smith | No | 3 | Level 3 | ◆ | Network Rfp Issued - 20/01/2023 - ◆ | In Progress | #6ab187 | 2023-01-20 | Future Task | 2023-01-20 | 0 | 0% |  | 2022-11-22 | 25 | 2022-10-23 | due in 60 days
Hosting & Network | #69D1C5 | Confirm Required Shared Service | Carl Smith | No | 2 | Level 2 | ▲ | Confirm Required Shared Service - 24/02/2023 - ▲ | In Progress | #6ab187 | 2023-02-24 | Future Task | 2023-02-24 | 0 | 0% |  | 2022-11-22 | 26 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Tom L2 | Carl Smith | No | 2 | Level 2 | ▲ | Tom L2 - 10/03/2023 - ▲ | In Progress | #6ab187 | 2023-03-10 | Future Task | 2023-03-10 | 0 | 0% |  | 2022-11-22 | 27 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Ph2 Landing Zone Ready | Carl Smith | No | 2 | Level 2 | ▲ | Ph2 Landing Zone Ready - 10/03/2023 - ▲ | In Progress | #6ab187 | 2023-03-10 | Future Task | 2023-03-10 | 0 | 0% |  | 2022-11-22 | 28 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Co Lo Supplier Selected | Carl Smith | No | 3 | Level 3 | ◆ | Co Lo Supplier Selected - 31/03/2023 - ◆ | In Progress | #6ab187 | 2023-03-31 | Future Task | 2023-03-31 | 0 | 0% |  | 2022-11-22 | 29 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Networks Hub Supplier Selected | Carl Smith | No | 3 | Level 3 | ◆ | Networks Hub Supplier Selected - 31/03/2023 - ◆ | In Progress | #6ab187 | 2023-03-31 | Future Task | 2023-03-31 | 0 | 0% |  | 2022-11-22 | 30 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Tom In Place With Migration Partner | Carl Smith | No | 2 | Level 2 | ▲ | Tom In Place With Migration Partner - 21/04/2023 - ▲ | In Progress | #6ab187 | 2023-04-21 | Future Task | 2023-04-21 | 0 | 0% |  | 2022-11-22 | 31 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | 1St Production App On Tranistion To Cloud | Carl Smith | No | 2 | Level 2 | ▲ | 1St Production App On Tranistion To Cloud - 28/04/2023 - ▲ | In Progress | #6ab187 | 2023-04-28 | Future Task | 2023-04-28 | 0 | 0% |  | 2022-11-22 | 32 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Wifi Implemented (As) | Carl Smith | No | 2 | Level 2 | ▲ | Wifi Implemented (As) - 19/05/2023 - ▲ | In Progress | #6ab187 | 2023-05-19 | Future Task | 2023-05-19 | 0 | 0% |  | 2022-11-22 | 33 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Co Lo Vendor Contracted | Carl Smith | No | 2 | Level 2 | ▲ | Co Lo Vendor Contracted - 30/06/2023 - ▲ | In Progress | #6ab187 | 2023-06-30 | Future Task | 2023-06-30 | 0 | 0% |  | 2022-11-22 | 34 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Network Vendor Contracted | Carl Smith | No | 1 | Level 1 | ✷ | Network Vendor Contracted - 30/06/2023 - ✷ | In Progress | #6ab187 | 2023-06-30 | Future Task | 2023-06-30 | 0 | 0% |  | 2022-11-22 | 35 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Ad Handover | Carl Smith | No | 2 | Level 2 | ▲ | Ad Handover - 17/11/2023 - ▲ | In Progress | #6ab187 | 2023-11-17 | Future Task | 2023-11-17 | 0 | 0% |  | 2022-11-22 | 36 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Network Ready | Carl Smith | No | 2 | Level 2 | ▲ | Network Ready - 24/11/2023 - ▲ | In Progress | #6ab187 | 2023-11-24 | Future Task | 2023-11-24 | 0 | 0% |  | 2022-11-22 | 37 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Co Lo Ready For Migration | Carl Smith | No | 2 | Level 2 | ▲ | Co Lo Ready For Migration - 24/11/2023 - ▲ | In Progress | #6ab187 | 2023-11-24 | Future Task | 2023-11-24 | 0 | 0% |  | 2022-11-22 | 38 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Business App Transformation Final Decision Point | Carl Smith | No | 3 | Level 3 | ◆ | Business App Transformation Final Decision Point - 29/12/2023 - ◆ | In Progress | #6ab187 | 2023-12-29 | Future Task | 2023-12-29 | 0 | 0% |  | 2022-11-22 | 39 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Wifi Implemented (0) | Carl Smith | No | 1 | Level 1 | ✷ | Wifi Implemented (0) - 01/03/2024 - ✷ | In Progress | #6ab187 | 2024-03-01 | Future Task | 2024-03-01 | 0 | 0% |  | 2022-11-22 | 40 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | All Applications Transitioned | Carl Smith | No | 1 | Level 1 | ✷ | All Applications Transitioned - 02/09/2024 - ✷ | In Progress | #6ab187 | 2024-09-02 | Future Task | 2024-09-02 | 0 | 0% |  | 2022-11-22 | 41 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | All Traffic Cutover To Target Network | Carl Smith | No | 1 | Level 1 | ✷ | All Traffic Cutover To Target Network - 02/09/2024 - ✷ | In Progress | #6ab187 | 2024-09-02 | Future Task | 2024-09-02 | 0 | 0% |  | 2022-11-22 | 42 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Capgemini Data Centres Decommissioned For Dlg | Carl Smith | No | 2 | Level 2 | ▲ | Capgemini Data Centres Decommissioned For Dlg - 27/12/2024 - ▲ | In Progress | #6ab187 | 2024-12-27 | Future Task | 2024-12-27 | 0 | 0% |  | 2022-11-22 | 43 | 2022-10-23 | due in over 90 days
Hosting & Network | #69D1C5 | Capgemini Networks Decommissioned For Dlg | Carl Smith | No | 2 | Level 2 | ▲ | Capgemini Networks Decommissioned For Dlg - 27/12/2024 - ▲ | In Progress | #6ab187 | 2024-12-27 | Future Task | 2024-12-27 | 0 | 0% |  | 2022-11-22 | 44 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Shortlist The Vendors For Rfp | Heidi Brearly | No | 3 | Level 3 | ◆ | Shortlist The Vendors For Rfp - 22/07/2022 - ◆ | Complete | #1c4e80 | 2022-07-22 | Complete | 2022-07-22 | 0 | 100% |  | 2022-11-22 | 45 | 2022-10-23 | Other Completed
Service Desk | #E6005B | Define Capgemini Kt Requirements | Heidi Brearly | No | 3 | Level 3 | ◆ | Define Capgemini Kt Requirements - 12/08/2022 - ◆ | Complete | #1c4e80 | 2022-08-12 | Complete | 2022-08-12 | 0 | 100% |  | 2022-11-22 | 46 | 2022-10-23 | Other Completed
Service Desk | #E6005B | Tom 1 Agreed (Exec Sourcing) | Heidi Brearly | No | 2 | Level 2 | ▲ | Tom 1 Agreed (Exec Sourcing) - 30/09/2022 - ▲ | Complete | #1c4e80 | 2022-09-30 | Complete | 2022-09-30 | 0 | 100% |  | 2022-11-22 | 47 | 2022-10-23 | Other Completed
Service Desk | #E6005B | Lessons Learnt Undertaken From Previous Procurement | Heidi Brearly | No | 3 | Level 3 | ◆ | Lessons Learnt Undertaken From Previous Procurement - 30/09/2022 - ◆ | Complete | #1c4e80 | 2022-09-30 | Complete | 2022-09-30 | 0 | 100% |  | 2022-11-22 | 48 | 2022-10-23 | Other Completed
Service Desk | #E6005B | Requirement Defined For Rfp | Heidi Brearly | No | 3 | Level 3 | ◆ | Requirement Defined For Rfp - 03/10/2022 - ◆ | Complete | #1c4e80 | 2022-10-03 | Complete | 2022-10-03 | 0 | 100% |  | 2022-11-22 | 49 | 2022-10-23 | Other Completed
Service Desk | #E6005B | Service Desk Commercial Strategy | Heidi Brearly | No | 2 | Level 2 | ▲ | Service Desk Commercial Strategy - 03/10/2022 - ▲ | Complete | #1c4e80 | 2022-10-03 | Complete | 2022-10-03 | 0 | 100% |  | 2022-11-22 | 50 | 2022-10-23 | Other Completed
Service Desk | #E6005B | Rfp Issued | Heidi Brearly | No | 2 | Level 2 | ▲ | Rfp Issued - 07/10/2022 - ▲ | Complete | #1c4e80 | 2022-10-07 | Complete | 2022-10-07 | 0 | 100% |  | 2022-11-22 | 51 | 2022-10-23 | Other Completed
Service Desk | #E6005B | Rebaselined Plan Based Ontom L1 | Heidi Brearly | No | 2 | Level 2 | ▲ | Rebaselined Plan Based Ontom L1 - 11/10/2022 - ▲ | Complete | #1c4e80 | 2022-10-11 | Complete | 2022-10-11 | 0 | 100% |  | 2022-11-22 | 52 | 2022-10-23 | Other Completed
Service Desk | #E6005B | Rebaselined Business Case Based On Tom L1 | Heidi Brearly | No | 2 | Level 2 | ▲ | Rebaselined Business Case Based On Tom L1 - 11/10/2022 - ▲ | Complete | #1c4e80 | 2022-10-11 | Complete | 2022-10-11 | 0 | 100% |  | 2022-11-22 | 53 | 2022-10-23 | Other Completed
Service Desk | #E6005B | Rfp Responses Received | Heidi Brearly | No | 3 | Level 3 | ◆ | Rfp Responses Received - 18/11/2022 - ◆ | Overdue | #EA0707 | 2022-11-18 | Future Task | 2022-11-18 | 0 | 0% |  | 2022-11-22 | 54 | 2022-10-23 | Overdue
Service Desk | #E6005B | Tom L1 Iterated (Inc. Sourcing) | Heidi Brearly | No | 2 | Level 2 | ▲ | Tom L1 Iterated (Inc. Sourcing) - 13/01/2023 - ▲ | In Progress | #6ab187 | 2023-01-13 | Future Task | 2023-01-13 | 0 | 0% |  | 2022-11-22 | 55 | 2022-10-23 | due in 60 days
Service Desk | #E6005B | Rebaselined Plan Based On Sourcing Model | Heidi Brearly | No | 2 | Level 2 | ▲ | Rebaselined Plan Based On Sourcing Model - 27/01/2023 - ▲ | In Progress | #6ab187 | 2023-01-27 | Future Task | 2023-01-27 | 0 | 0% |  | 2022-11-22 | 56 | 2022-10-23 | due in 90 days
Service Desk | #E6005B | Rebaselined Business Case Based On Sourcing Model | Heidi Brearly | No | 2 | Level 2 | ▲ | Rebaselined Business Case Based On Sourcing Model - 27/01/2023 - ▲ | In Progress | #6ab187 | 2023-01-27 | Future Task | 2023-01-27 | 0 | 0% |  | 2022-11-22 | 57 | 2022-10-23 | due in 90 days
Service Desk | #E6005B | Vendor Selected | Heidi Brearly | No | 2 | Level 2 | ▲ | Vendor Selected - 17/02/2023 - ▲ | In Progress | #6ab187 | 2023-02-17 | Future Task | 2023-02-17 | 0 | 0% |  | 2022-11-22 | 58 | 2022-10-23 | due in 90 days
Service Desk | #E6005B | Engage With Capgemini On Exit | Heidi Brearly | No | 1 | Level 1 | ✷ | Engage With Capgemini On Exit - 14/04/2023 - ✷ | In Progress | #6ab187 | 2023-04-14 | Future Task | 2023-04-14 | 0 | 0% |  | 2022-11-22 | 59 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Supplier Contracted | Heidi Brearly | No | 2 | Level 2 | ▲ | Supplier Contracted - 28/04/2023 - ▲ | In Progress | #6ab187 | 2023-04-28 | Future Task | 2023-04-28 | 0 | 0% |  | 2022-11-22 | 60 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Capgemini Exit Date Agreed | Heidi Brearly | Yes | 2 | Level 2 | ▲ | Capgemini Exit Date Agreed - 19/05/2023 - ▲ | At Risk | #FFBF00 | 2023-05-19 | Future Task | 2023-05-19 | 0 | 0% |  | 2022-11-22 | 61 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Transition Plan Agreed | Heidi Brearly | No | 2 | Level 2 | ▲ | Transition Plan Agreed - 16/06/2023 - ▲ | In Progress | #6ab187 | 2023-06-16 | Future Task | 2023-06-16 | 0 | 0% |  | 2022-11-22 | 62 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Rebaselined Plan Based On Contract Agreement | Heidi Brearly | No | 2 | Level 2 | ▲ | Rebaselined Plan Based On Contract Agreement - 16/06/2023 - ▲ | In Progress | #6ab187 | 2023-06-16 | Future Task | 2023-06-16 | 0 | 0% |  | 2022-11-22 | 63 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Rebaselined Business Case Based On Contract Agreement | Heidi Brearly | No | 2 | Level 2 | ▲ | Rebaselined Business Case Based On Contract Agreement - 16/06/2023 - ▲ | In Progress | #6ab187 | 2023-06-16 | Future Task | 2023-06-16 | 0 | 0% |  | 2022-11-22 | 64 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Tom L2 Agreed (Service Design And Support Model) | Heidi Brearly | No | 2 | Level 2 | ▲ | Tom L2 Agreed (Service Design And Support Model) - 30/06/2023 - ▲ | In Progress | #6ab187 | 2023-06-30 | Future Task | 2023-06-30 | 0 | 0% |  | 2022-11-22 | 65 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Complete Run Cost Model | Heidi Brearly | No | 2 | Level 2 | ▲ | Complete Run Cost Model - 30/06/2023 - ▲ | In Progress | #6ab187 | 2023-06-30 | Future Task | 2023-06-30 | 0 | 0% |  | 2022-11-22 | 66 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Ovt Start | Heidi Brearly | No | 2 | Level 2 | ▲ | Ovt Start - 01/09/2023 - ▲ | In Progress | #6ab187 | 2023-09-01 | Future Task | 2023-09-01 | 0 | 0% |  | 2022-11-22 | 67 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Define The Service Desk Comms Strategy | Heidi Brearly | No | 2 | Level 2 | ▲ | Define The Service Desk Comms Strategy - 29/09/2023 - ▲ | In Progress | #6ab187 | 2023-09-29 | Future Task | 2023-09-29 | 0 | 0% |  | 2022-11-22 | 68 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Itsm Build And Integration Completed | Heidi Brearly | No | 2 | Level 2 | ▲ | Itsm Build And Integration Completed - 06/10/2023 - ▲ | In Progress | #6ab187 | 2023-10-06 | Future Task | 2023-10-06 | 0 | 0% |  | 2022-11-22 | 69 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Service Ready For Transition | Heidi Brearly | No | 1 | Level 1 | ✷ | Service Ready For Transition - 27/10/2023 - ✷ | In Progress | #6ab187 | 2023-10-27 | Future Task | 2023-10-27 | 0 | 0% |  | 2022-11-22 | 70 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Delivery Comms Completed | Heidi Brearly | No | 2 | Level 2 | ▲ | Delivery Comms Completed - 17/11/2023 - ▲ | In Progress | #6ab187 | 2023-11-17 | Future Task | 2023-11-17 | 0 | 0% |  | 2022-11-22 | 71 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Ovt Completed | Heidi Brearly | No | 2 | Level 2 | ▲ | Ovt Completed - 17/11/2023 - ▲ | In Progress | #6ab187 | 2023-11-17 | Future Task | 2023-11-17 | 0 | 0% |  | 2022-11-22 | 72 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Access Revoked For Legacy Service Desk | Heidi Brearly | No | 3 | Level 3 | ◆ | Access Revoked For Legacy Service Desk - 23/02/2024 - ◆ | In Progress | #6ab187 | 2024-02-23 | Future Task | 2024-02-23 | 0 | 0% |  | 2022-11-22 | 73 | 2022-10-23 | due in over 90 days
Service Desk | #E6005B | Service Desk Tower Decommissioned On Exit From Capgemini Completed | Heidi Brearly | No | 1 | Level 1 | ✷ | Service Desk Tower Decommissioned On Exit From Capgemini Completed - 15/03/2024 - ✷ | In Progress | #6ab187 | 2024-03-15 | Future Task | 2024-03-15 | 0 | 0% |  | 2022-11-22 | 74 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | App Packaging Service Contract | Richard Higgins | No | 2 | Level 2 | ▲ | App Packaging Service Contract - 19/08/2022 - ▲ | Complete | #1c4e80 | 2022-08-19 | Complete | 2022-08-19 | 0 | 100% |  | 2022-11-22 | 75 | 2022-10-23 | Other Completed
Euc | #8980F5 | Develop Dlg Avd | Richard Higgins | No | 2 | Level 2 | ▲ | Develop Dlg Avd - 19/08/2022 - ▲ | Complete | #1c4e80 | 2022-08-19 | Complete | 2022-08-19 | 0 | 100% |  | 2022-11-22 | 76 | 2022-10-23 | Other Completed
Euc | #8980F5 | Si Completed | Richard Higgins | No | 2 | Level 2 | ▲ | Si Completed - 19/08/2022 - ▲ | Complete | #1c4e80 | 2022-08-19 | Complete | 2022-08-19 | 0 | 100% |  | 2022-11-22 | 77 | 2022-10-23 | Other Completed
Euc | #8980F5 | Servicenow Go Live | Richard Higgins | No | 2 | Level 2 | ▲ | Servicenow Go Live - 26/08/2022 - ▲ | Complete | #1c4e80 | 2022-08-26 | Complete | 2022-08-26 | 0 | 100% |  | 2022-11-22 | 78 | 2022-10-23 | Other Completed
Euc | #8980F5 | App Packaging Service Starts | Richard Higgins | No | 2 | Level 2 | ▲ | App Packaging Service Starts - 09/09/2022 - ▲ | Complete | #1c4e80 | 2022-09-09 | Complete | 2022-09-09 | 0 | 100% |  | 2022-11-22 | 79 | 2022-10-23 | Other Completed
Euc | #8980F5 | Start App Conversion | Richard Higgins | No | 2 | Level 2 | ▲ | Start App Conversion - 30/09/2022 - ▲ | Complete | #1c4e80 | 2022-09-30 | Complete | 2022-09-30 | 0 | 100% |  | 2022-11-22 | 80 | 2022-10-23 | Other Completed
Euc | #8980F5 | Start Pilot For Business Areas | Richard Higgins | No | 2 | Level 2 | ▲ | Start Pilot For Business Areas - 07/10/2022 - ▲ | Complete | #1c4e80 | 2022-10-07 | Complete | 2022-10-07 | 0 | 100% |  | 2022-11-22 | 81 | 2022-10-23 | Other Completed
Euc | #8980F5 | Start Conversion Of Physical Desktops | Richard Higgins | No | 2 | Level 2 | ▲ | Start Conversion Of Physical Desktops - 07/10/2022 - ▲ | Complete | #1c4e80 | 2022-10-07 | Complete | 2022-10-07 | 0 | 100% |  | 2022-11-22 | 82 | 2022-10-23 | Other Completed
Euc | #8980F5 | Start Euda Discovery | Richard Higgins | No | 2 | Level 2 | ▲ | Start Euda Discovery - 04/11/2022 - ▲ | Overdue | #EA0707 | 2022-11-04 | Future Task | 2022-11-04 | 0 | 0% |  | 2022-11-22 | 83 | 2022-10-23 | Overdue
Euc | #8980F5 | Model Office Fit Out | Richard Higgins | No | 2 | Level 2 | ▲ | Model Office Fit Out - 16/11/2022 - ▲ | Overdue | #EA0707 | 2022-11-16 | Future Task | 2022-11-16 | 0 | 0% |  | 2022-11-22 | 84 | 2022-10-23 | Overdue
Euc | #8980F5 | Start Migration Of Bu To Avd | Richard Higgins | No | 2 | Level 2 | ▲ | Start Migration Of Bu To Avd - 25/11/2022 - ▲ | In Progress | #6ab187 | 2022-11-25 | Future Task | 2022-11-25 | 0 | 0% |  | 2022-11-22 | 85 | 2022-10-23 | due in 30 days
Euc | #8980F5 | Start Data Migration Discovery | Richard Higgins | No | 2 | Level 2 | ▲ | Start Data Migration Discovery - 02/12/2022 - ▲ | In Progress | #6ab187 | 2022-12-02 | Future Task | 2022-12-02 | 0 | 0% |  | 2022-11-22 | 86 | 2022-10-23 | due in 30 days
Euc | #8980F5 | Agree Tom For Other Service Items | Richard Higgins | No | 2 | Level 2 | ▲ | Agree Tom For Other Service Items - 06/01/2023 - ▲ | In Progress | #6ab187 | 2023-01-06 | Future Task | 2023-01-06 | 0 | 0% |  | 2022-11-22 | 87 | 2022-10-23 | due in 60 days
Euc | #8980F5 | Data Analysis | Richard Higgins | Yes | 2 | Level 2 | ▲ | Data Analysis - 13/01/2023 - ▲ | At Risk | #FFBF00 | 2023-01-13 | Future Task | 2023-01-13 | 0 | 0% |  | 2022-11-22 | 88 | 2022-10-23 | due in 60 days
Euc | #8980F5 | Euda Analysis | Richard Higgins | No | 2 | Level 2 | ▲ | Euda Analysis - 20/01/2023 - ▲ | In Progress | #6ab187 | 2023-01-20 | Future Task | 2023-01-20 | 0 | 0% |  | 2022-11-22 | 89 | 2022-10-23 | due in 60 days
Euc | #8980F5 | High Density Wireless Network Services | Richard Higgins | No | 2 | Level 2 | ▲ | High Density Wireless Network Services - 27/01/2023 - ▲ | In Progress | #6ab187 | 2023-01-27 | Future Task | 2023-01-27 | 0 | 0% |  | 2022-11-22 | 90 | 2022-10-23 | due in 90 days
Euc | #8980F5 | Agree Data Migration Rules | Richard Higgins | No | 2 | Level 2 | ▲ | Agree Data Migration Rules - 10/02/2023 - ▲ | In Progress | #6ab187 | 2023-02-10 | Future Task | 2023-02-10 | 0 | 0% |  | 2022-11-22 | 91 | 2022-10-23 | due in 90 days
Euc | #8980F5 | Agree Euda Approach | Richard Higgins | Yes | 2 | Level 2 | ▲ | Agree Euda Approach - 28/02/2023 - ▲ | At Risk | #FFBF00 | 2023-02-28 | Future Task | 2023-02-28 | 0 | 0% |  | 2022-11-22 | 92 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Services Contract Tom For Other Service Items | Richard Higgins | No | 2 | Level 2 | ▲ | Services Contract Tom For Other Service Items - 17/03/2023 - ▲ | In Progress | #6ab187 | 2023-03-17 | Future Task | 2023-03-17 | 0 | 0% |  | 2022-11-22 | 93 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Finish Desktop Conversion | Richard Higgins | No | 2 | Level 2 | ▲ | Finish Desktop Conversion - 31/03/2023 - ▲ | In Progress | #6ab187 | 2023-03-31 | Future Task | 2023-03-31 | 0 | 0% |  | 2022-11-22 | 94 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Start Deployment Of Services To In Scope Locations | Richard Higgins | No | 2 | Level 2 | ▲ | Start Deployment Of Services To In Scope Locations - 14/04/2023 - ▲ | In Progress | #6ab187 | 2023-04-14 | Future Task | 2023-04-14 | 0 | 0% |  | 2022-11-22 | 95 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | End Of Business Pilot Dlg Avd | Richard Higgins | No | 2 | Level 2 | ▲ | End Of Business Pilot Dlg Avd - 28/04/2023 - ▲ | In Progress | #6ab187 | 2023-04-28 | Future Task | 2023-04-28 | 0 | 0% |  | 2022-11-22 | 96 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Room Booking Service Remdiation | Richard Higgins | No | 2 | Level 2 | ▲ | Room Booking Service Remdiation - 26/05/2023 - ▲ | In Progress | #6ab187 | 2023-05-26 | Future Task | 2023-05-26 | 0 | 0% |  | 2022-11-22 | 97 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Wireless Print Service | Richard Higgins | No | 2 | Level 2 | ▲ | Wireless Print Service - 26/05/2023 - ▲ | In Progress | #6ab187 | 2023-05-26 | Future Task | 2023-05-26 | 0 | 0% |  | 2022-11-22 | 98 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Local Internet Telephony Services | Richard Higgins | No | 2 | Level 2 | ▲ | Local Internet Telephony Services - 26/05/2023 - ▲ | In Progress | #6ab187 | 2023-05-26 | Future Task | 2023-05-26 | 0 | 0% |  | 2022-11-22 | 99 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Local Thin Client Services | Richard Higgins | No | 2 | Level 2 | ▲ | Local Thin Client Services - 26/05/2023 - ▲ | In Progress | #6ab187 | 2023-05-26 | Future Task | 2023-05-26 | 0 | 0% |  | 2022-11-22 | 100 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Data Migration Complete | Richard Higgins | No | 2 | Level 2 | ▲ | Data Migration Complete - 25/08/2023 - ▲ | In Progress | #6ab187 | 2023-08-25 | Future Task | 2023-08-25 | 0 | 0% |  | 2022-11-22 | 101 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Euda Remediation Complete | Richard Higgins | No | 2 | Level 2 | ▲ | Euda Remediation Complete - 22/09/2023 - ▲ | In Progress | #6ab187 | 2023-09-22 | Future Task | 2023-09-22 | 0 | 0% |  | 2022-11-22 | 102 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | End Of Avd Migration | Richard Higgins | No | 2 | Level 2 | ▲ | End Of Avd Migration - 13/10/2023 - ▲ | In Progress | #6ab187 | 2023-10-13 | Future Task | 2023-10-13 | 0 | 0% |  | 2022-11-22 | 103 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | End Of App Conversion | Richard Higgins | No | 2 | Level 2 | ▲ | End Of App Conversion - 20/10/2023 - ▲ | In Progress | #6ab187 | 2023-10-20 | Future Task | 2023-10-20 | 0 | 0% |  | 2022-11-22 | 104 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | O365 Messaging Complete | Richard Higgins | No | 2 | Level 2 | ▲ | O365 Messaging Complete - 24/11/2023 - ▲ | In Progress | #6ab187 | 2023-11-24 | Future Task | 2023-11-24 | 0 | 0% |  | 2022-11-22 | 105 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Physical Desktop Replacement | Richard Higgins | No | 2 | Level 2 | ▲ | Physical Desktop Replacement - 22/12/2023 - ▲ | In Progress | #6ab187 | 2023-12-22 | Future Task | 2023-12-22 | 0 | 0% |  | 2022-11-22 | 106 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Office Break Fix Service | Richard Higgins | No | 2 | Level 2 | ▲ | Office Break Fix Service - 22/12/2023 - ▲ | In Progress | #6ab187 | 2023-12-22 | Future Task | 2023-12-22 | 0 | 0% |  | 2022-11-22 | 107 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Audio Visual Support Service | Richard Higgins | No | 2 | Level 2 | ▲ | Audio Visual Support Service - 22/12/2023 - ▲ | In Progress | #6ab187 | 2023-12-22 | Future Task | 2023-12-22 | 0 | 0% |  | 2022-11-22 | 108 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Deskside Support Services | Richard Higgins | No | 2 | Level 2 | ▲ | Deskside Support Services - 22/12/2023 - ▲ | In Progress | #6ab187 | 2023-12-22 | Future Task | 2023-12-22 | 0 | 0% |  | 2022-11-22 | 109 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | Migration Of Ad To Cloud | Richard Higgins | No | 2 | Level 2 | ▲ | Migration Of Ad To Cloud - 22/12/2023 - ▲ | In Progress | #6ab187 | 2023-12-22 | Future Task | 2023-12-22 | 0 | 0% |  | 2022-11-22 | 110 | 2022-10-23 | due in over 90 days
Euc | #8980F5 | File Shares Migrated | Richard Higgins | No | 1 | Level 1 | ✷ | File Shares Migrated - 01/03/2024 - ✷ | In Progress | #6ab187 | 2024-03-01 | Future Task | 2024-03-01 | 0 | 0% |  | 2022-11-22 | 111 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Capgemini Wors/Wo | Paul Cochrane | No | 3 | Level 3 | ◆ | Capgemini Wors/Wo - 20/05/2022 - ◆ | Complete | #1c4e80 | 2022-05-20 | Complete | 2022-05-20 | 0 | 100% |  | 2022-11-22 | 112 | 2022-10-23 | Other Completed
Security | #FFBF00 | Lr Forecast Commercials Approved | Paul Cochrane | No | 2 | Level 2 | ▲ | Lr Forecast Commercials Approved - 20/05/2022 - ▲ | Complete | #1c4e80 | 2022-05-20 | Complete | 2022-05-20 | 0 | 100% |  | 2022-11-22 | 113 | 2022-10-23 | Other Completed
Security | #FFBF00 | Lr Pilot Commenced | Paul Cochrane | No | 2 | Level 2 | ▲ | Lr Pilot Commenced - 15/08/2022 - ▲ | Complete | #1c4e80 | 2022-08-15 | Complete | 2022-08-15 | 0 | 100% |  | 2022-11-22 | 114 | 2022-10-23 | Other Completed
Security | #FFBF00 | Capgemini Wors/Wo | Paul Cochrane | No | 3 | Level 3 | ◆ | Capgemini Wors/Wo - 02/09/2022 - ◆ | Complete | #1c4e80 | 2022-09-02 | Complete | 2022-09-02 | 0 | 100% |  | 2022-11-22 | 115 | 2022-10-23 | Other Completed
Security | #FFBF00 | Ca Forecast Commercials Approved | Paul Cochrane | No | 2 | Level 2 | ▲ | Ca Forecast Commercials Approved - 30/09/2022 - ▲ | Complete | #1c4e80 | 2022-09-30 | Complete | 2022-09-30 | 0 | 100% |  | 2022-11-22 | 116 | 2022-10-23 | Other Completed
Security | #FFBF00 | Ca Pilot Commenced | Paul Cochrane | Yes | 2 | Level 2 | ▲ | Ca Pilot Commenced - 21/10/2022 - ▲ | At Risk | #FFBF00 | 2022-10-21 | Complete | 2022-10-21 | 0 | 100% |  | 2022-11-22 | 117 | 2022-10-23 | Other Completed
Security | #FFBF00 | Logrhythm Pilots Complete | Paul Cochrane | No | 2 | Level 2 | ▲ | Logrhythm Pilots Complete - 04/11/2022 - ▲ | Overdue | #EA0707 | 2022-11-04 | Future Task | 2022-11-04 | 0 | 0% |  | 2022-11-22 | 118 | 2022-10-23 | Overdue
Security | #FFBF00 | Venafi Forecast Commercials Approved | Paul Cochrane | No | 2 | Level 2 | ▲ | Venafi Forecast Commercials Approved - 18/11/2022 - ▲ | Overdue | #EA0707 | 2022-11-18 | Future Task | 2022-11-18 | 0 | 0% |  | 2022-11-22 | 119 | 2022-10-23 | Overdue
Security | #FFBF00 | Logrhythm Design And Build Complete | Paul Cochrane | No | 2 | Level 2 | ▲ | Logrhythm Design And Build Complete - 02/12/2022 - ▲ | In Progress | #6ab187 | 2022-12-02 | Future Task | 2022-12-02 | 0 | 0% |  | 2022-11-22 | 120 | 2022-10-23 | due in 30 days
Security | #FFBF00 | Capgemini Wors/Wo | Paul Cochrane | No | 3 | Level 3 | ◆ | Capgemini Wors/Wo - 16/12/2022 - ◆ | In Progress | #6ab187 | 2022-12-16 | Future Task | 2022-12-16 | 0 | 0% |  | 2022-11-22 | 121 | 2022-10-23 | due in 30 days
Security | #FFBF00 | Cyberark Pilots Complete | Paul Cochrane | No | 2 | Level 2 | ▲ | Cyberark Pilots Complete - 06/01/2023 - ▲ | In Progress | #6ab187 | 2023-01-06 | Future Task | 2023-01-06 | 0 | 0% |  | 2022-11-22 | 122 | 2022-10-23 | due in 60 days
Security | #FFBF00 | Logrhythm Migration Complete | Paul Cochrane | No | 2 | Level 2 | ▲ | Logrhythm Migration Complete - 10/03/2023 - ▲ | In Progress | #6ab187 | 2023-03-10 | Future Task | 2023-03-10 | 0 | 0% |  | 2022-11-22 | 123 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Venafi Pilot Complete | Paul Cochrane | No | 2 | Level 2 | ▲ | Venafi Pilot Complete - 17/03/2023 - ▲ | In Progress | #6ab187 | 2023-03-17 | Future Task | 2023-03-17 | 0 | 0% |  | 2022-11-22 | 124 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Cyberark Design And Build Complete | Paul Cochrane | No | 2 | Level 2 | ▲ | Cyberark Design And Build Complete - 17/03/2023 - ▲ | In Progress | #6ab187 | 2023-03-17 | Future Task | 2023-03-17 | 0 | 0% |  | 2022-11-22 | 125 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Venafi Design And Build Complete | Paul Cochrane | No | 2 | Level 2 | ▲ | Venafi Design And Build Complete - 31/03/2023 - ▲ | In Progress | #6ab187 | 2023-03-31 | Future Task | 2023-03-31 | 0 | 0% |  | 2022-11-22 | 126 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Logrhythm Decommissioned From Dc | Paul Cochrane | No | 2 | Level 2 | ▲ | Logrhythm Decommissioned From Dc - 07/07/2023 - ▲ | In Progress | #6ab187 | 2023-07-07 | Future Task | 2023-07-07 | 0 | 0% |  | 2022-11-22 | 127 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Forescout And Skybox Solution Decision Point | Paul Cochrane | No | 3 | Level 3 | ◆ | Forescout And Skybox Solution Decision Point - 21/07/2023 - ◆ | In Progress | #6ab187 | 2023-07-21 | Future Task | 2023-07-21 | 0 | 0% |  | 2022-11-22 | 128 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Venafi Migration Complete | Paul Cochrane | No | 2 | Level 2 | ▲ | Venafi Migration Complete - 21/07/2023 - ▲ | In Progress | #6ab187 | 2023-07-21 | Future Task | 2023-07-21 | 0 | 0% |  | 2022-11-22 | 129 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Cyberark Migration Complete | Paul Cochrane | No | 3 | Level 3 | ◆ | Cyberark Migration Complete - 01/09/2023 - ◆ | In Progress | #6ab187 | 2023-09-01 | Future Task | 2023-09-01 | 0 | 0% |  | 2022-11-22 | 130 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Cyberark Decommissioned From Dc | Paul Cochrane | No | 3 | Level 3 | ◆ | Cyberark Decommissioned From Dc - 27/10/2023 - ◆ | In Progress | #6ab187 | 2023-10-27 | Future Task | 2023-10-27 | 0 | 0% |  | 2022-11-22 | 131 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Venafi Decommissioned From Dc | Paul Cochrane | No | 3 | Level 3 | ◆ | Venafi Decommissioned From Dc - 10/11/2023 - ◆ | In Progress | #6ab187 | 2023-11-10 | Future Task | 2023-11-10 | 0 | 0% |  | 2022-11-22 | 132 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Requirements Gathering | Raj Raghav | No | 3 | Level 3 | ◆ | Requirements Gathering - 22/07/2022 - ◆ | Complete | #1c4e80 | 2022-07-22 | Complete | 2022-07-22 | 0 | 100% |  | 2022-11-22 | 133 | 2022-10-23 | Other Completed
Security | #FFBF00 | Dependency Workshops | Raj Raghav | No | 3 | Level 3 | ◆ | Dependency Workshops - 22/07/2022 - ◆ | Complete | #1c4e80 | 2022-07-22 | Complete | 2022-07-22 | 0 | 100% |  | 2022-11-22 | 134 | 2022-10-23 | Other Completed
Security | #FFBF00 | E5 Step Up Licences Procured | Raj Raghav | No | 3 | Level 3 | ◆ | E5 Step Up Licences Procured - 22/07/2022 - ◆ | Complete | #1c4e80 | 2022-07-22 | Complete | 2022-07-22 | 0 | 100% |  | 2022-11-22 | 135 | 2022-10-23 | Other Completed
Security | #FFBF00 | Dlp Design Completed | Raj Raghav | No | 3 | Level 3 | ◆ | Dlp Design Completed - 26/08/2022 - ◆ | Complete | #1c4e80 | 2022-08-26 | Complete | 2022-08-26 | 0 | 100% |  | 2022-11-22 | 136 | 2022-10-23 | Other Completed
Security | #FFBF00 | Epp & Edr Design Completed | Raj Raghav | No | 3 | Level 3 | ◆ | Epp & Edr Design Completed - 02/09/2022 - ◆ | Complete | #1c4e80 | 2022-09-02 | Complete | 2022-09-02 | 0 | 100% |  | 2022-11-22 | 137 | 2022-10-23 | Other Completed
Security | #FFBF00 | Email Hygiene Design Completed | Raj Raghav | No | 3 | Level 3 | ◆ | Email Hygiene Design Completed - 30/09/2022 - ◆ | Overdue | #EA0707 | 2022-09-30 | Late | 2022-09-30 | 0 | 0% |  | 2022-11-22 | 138 | 2022-10-23 | Overdue
Security | #FFBF00 | Cloud App Security Design Completed | Raj Raghav | No | 3 | Level 3 | ◆ | Cloud App Security Design Completed - 18/10/2022 - ◆ | Overdue | #EA0707 | 2022-10-18 | Late | 2022-10-18 | 0 | 0% |  | 2022-11-22 | 139 | 2022-10-23 | Overdue
Security | #FFBF00 | Dlp Pilot Completed | Raj Raghav | No | 2 | Level 2 | ▲ | Dlp Pilot Completed - 25/11/2022 - ▲ | In Progress | #6ab187 | 2022-11-25 | Future Task | 2022-11-25 | 0 | 0% |  | 2022-11-22 | 140 | 2022-10-23 | due in 30 days
Security | #FFBF00 | Design Phase Completed | Raj Raghav | Yes | 2 | Level 2 | ▲ | Design Phase Completed - 23/12/2022 - ▲ | At Risk | #FFBF00 | 2022-12-23 | Future Task | 2022-12-23 | 0 | 0% |  | 2022-11-22 | 141 | 2022-10-23 | due in 60 days
Security | #FFBF00 | Email Hygiene Completed | Raj Raghav | No | 3 | Level 3 | ◆ | Email Hygiene Completed - 03/02/2023 - ◆ | In Progress | #6ab187 | 2023-02-03 | Future Task | 2023-02-03 | 0 | 0% |  | 2022-11-22 | 142 | 2022-10-23 | due in 90 days
Security | #FFBF00 | Cloud App Security Pilot Completed | Raj Raghav | No | 3 | Level 3 | ◆ | Cloud App Security Pilot Completed - 24/02/2023 - ◆ | In Progress | #6ab187 | 2023-02-24 | Future Task | 2023-02-24 | 0 | 0% |  | 2022-11-22 | 143 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Dlp Migrated | Raj Raghav | No | 3 | Level 3 | ◆ | Dlp Migrated - 03/03/2023 - ◆ | In Progress | #6ab187 | 2023-03-03 | Future Task | 2023-03-03 | 0 | 0% |  | 2022-11-22 | 144 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Edp & Edr Pilot Completed | Raj Raghav | No | 3 | Level 3 | ◆ | Edp & Edr Pilot Completed - 17/03/2023 - ◆ | In Progress | #6ab187 | 2023-03-17 | Future Task | 2023-03-17 | 0 | 0% |  | 2022-11-22 | 145 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Cloud App Security Migrated | Raj Raghav | No | 3 | Level 3 | ◆ | Cloud App Security Migrated - 19/05/2023 - ◆ | In Progress | #6ab187 | 2023-05-19 | Future Task | 2023-05-19 | 0 | 0% |  | 2022-11-22 | 146 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Pilot Phase Completed | Raj Raghav | No | 3 | Level 3 | ◆ | Pilot Phase Completed - 30/06/2023 - ◆ | In Progress | #6ab187 | 2023-06-30 | Future Task | 2023-06-30 | 0 | 0% |  | 2022-11-22 | 147 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Legacy Email Routing. Email Hygiene & Cass Entries Removed | Raj Raghav | No | 3 | Level 3 | ◆ | Legacy Email Routing. Email Hygiene & Cass Entries Removed - 18/08/2023 - ◆ | In Progress | #6ab187 | 2023-08-18 | Future Task | 2023-08-18 | 0 | 0% |  | 2022-11-22 | 148 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Epp & Edr Migrated | Raj Raghav | No | 3 | Level 3 | ◆ | Epp & Edr Migrated - 08/09/2023 - ◆ | In Progress | #6ab187 | 2023-09-08 | Future Task | 2023-09-08 | 0 | 0% |  | 2022-11-22 | 149 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Legacy Dlp & Aip Decommissioned | Raj Raghav | No | 3 | Level 3 | ◆ | Legacy Dlp & Aip Decommissioned - 08/09/2023 - ◆ | In Progress | #6ab187 | 2023-09-08 | Future Task | 2023-09-08 | 0 | 0% |  | 2022-11-22 | 150 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Legacy Epp & Edr Decommissioned | Raj Raghav | No | 3 | Level 3 | ◆ | Legacy Epp & Edr Decommissioned - 01/12/2023 - ◆ | In Progress | #6ab187 | 2023-12-01 | Future Task | 2023-12-01 | 0 | 0% |  | 2022-11-22 | 151 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Migration Of Security Tools Completed | Raj Raghav | No | 1 | Level 1 | ✷ | Migration Of Security Tools Completed - 22/12/2023 - ✷ | In Progress | #6ab187 | 2023-12-22 | Future Task | 2023-12-22 | 0 | 0% |  | 2022-11-22 | 152 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Symantec Estate Decommissioned | Raj Raghav | No | 2 | Level 2 | ▲ | Symantec Estate Decommissioned - 22/12/2023 - ▲ | In Progress | #6ab187 | 2023-12-22 | Future Task | 2023-12-22 | 0 | 0% |  | 2022-11-22 | 153 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Project Abient Completed/Closed | Raj Raghav | No | 2 | Level 2 | ▲ | Project Abient Completed/Closed - 20/12/2024 - ▲ | In Progress | #6ab187 | 2024-12-20 | Future Task | 2024-12-20 | 0 | 0% |  | 2022-11-22 | 154 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Kick Off Initiated | Gerrad Olisa-Ashar | No | 3 | Level 3 | ◆ | Kick Off Initiated - 01/08/2022 - ◆ | Complete | #1c4e80 | 2022-08-01 | Complete | 2022-08-01 | 0 | 100% |  | 2022-11-22 | 155 | 2022-10-23 | Other Completed
Security | #FFBF00 | As Is State Baselined | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | As Is State Baselined - 03/10/2022 - ▲ | Complete | #1c4e80 | 2022-10-03 | Complete | 2022-10-03 | 0 | 100% |  | 2022-11-22 | 156 | 2022-10-23 | Other Completed
Security | #FFBF00 | Rfi/Rfp Reqs Agreed | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | Rfi/Rfp Reqs Agreed - 30/09/2022 - ▲ | Complete | #1c4e80 | 2022-09-30 | Complete | 2022-09-30 | 0 | 100% |  | 2022-11-22 | 157 | 2022-10-23 | Other Completed
Security | #FFBF00 | Rigel Rfp Issued | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | Rigel Rfp Issued - 10/10/2022 - ▲ | Overdue | #EA0707 | 2022-10-10 | Late | 2022-10-10 | 0 | 0% |  | 2022-11-22 | 158 | 2022-10-23 | Overdue
Security | #FFBF00 | Target State Defined | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | Target State Defined - 25/11/2022 - ▲ | In Progress | #6ab187 | 2022-11-25 | Future Task | 2022-11-25 | 0 | 0% |  | 2022-11-22 | 159 | 2022-10-23 | due in 30 days
Security | #FFBF00 | Rigel Vendor Selected | Gerrad Olisa-Ashar | Yes | 2 | Level 2 | ▲ | Rigel Vendor Selected - 02/12/2022 - ▲ | At Risk | #FFBF00 | 2022-12-02 | Future Task | 2022-12-02 | 0 | 0% |  | 2022-11-22 | 160 | 2022-10-23 | due in 30 days
Security | #FFBF00 | Internal Capability Commences | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | Internal Capability Commences - 30/12/2022 - ▲ | In Progress | #6ab187 | 2022-12-30 | Future Task | 2022-12-30 | 0 | 0% |  | 2022-11-22 | 161 | 2022-10-23 | due in 60 days
Security | #FFBF00 | Supplier Contracted (Tbc) | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | Supplier Contracted (Tbc) - 24/02/2023 - ▲ | In Progress | #6ab187 | 2023-02-24 | Future Task | 2023-02-24 | 0 | 0% |  | 2022-11-22 | 162 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Kt And Training Commence | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | Kt And Training Commence - 31/03/2023 - ▲ | In Progress | #6ab187 | 2023-03-31 | Future Task | 2023-03-31 | 0 | 0% |  | 2022-11-22 | 163 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Kt And Training Completed | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | Kt And Training Completed - 22/09/2023 - ▲ | In Progress | #6ab187 | 2023-09-22 | Future Task | 2023-09-22 | 0 | 0% |  | 2022-11-22 | 164 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Internal Capability Built | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | Internal Capability Built - 22/09/2023 - ▲ | In Progress | #6ab187 | 2023-09-22 | Future Task | 2023-09-22 | 0 | 0% |  | 2022-11-22 | 165 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Dual Running Commences Eg. Soc | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | Dual Running Commences Eg. Soc - 29/09/2023 - ▲ | In Progress | #6ab187 | 2023-09-29 | Future Task | 2023-09-29 | 0 | 0% |  | 2022-11-22 | 166 | 2022-10-23 | due in over 90 days
Security | #FFBF00 | Dual Running Completed Eg. Soc | Gerrad Olisa-Ashar | No | 2 | Level 2 | ▲ | Dual Running Completed Eg. Soc - 20/12/2024 - ▲ | In Progress | #6ab187 | 2024-12-20 | Future Task | 2024-12-20 | 0 | 0% |  | 2022-11-22 | 167 | 2022-10-23 | due in over 90 days