## Data
Status | Milestone Level | Task Name | Duration | Start | Finish | % Complete | Predecessors | Tower | Resource Names | Constraint Type | Task Mode | Notes | Baseline1 Finish
Late |  | MIDGARD | 695 days | Fri 29/04/22 | Fri 27/12/24 | 0% |  |  |  | As Soon As Possible | Auto Scheduled |  | NA
Future Task |  | Key Milestones (level 1) | 361 days | Fri 14/04/23 | Mon 02/09/24 | 0% |  |  |  | As Soon As Possible | Auto Scheduled |  | NA
Future Task |  | Engage with Capgemini for exit transition plan | 0 days | Fri 14/04/23 | Fri 14/04/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task |  | Network vendor contracted | 0 days | Fri 30/06/23 | Fri 30/06/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task |  | Service desk transitioned | 0 days | Fri 27/10/23 | Fri 27/10/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task |  | Migration of security tools completed | 0 days | Fri 22/12/23 | Fri 22/12/23 | 0% |  | Security Abient | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task |  | File Shares migrated | 0 days | Fri 01/03/24 | Fri 01/03/24 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task |  | WiFi implemented | 0 days | Fri 01/03/24 | Fri 01/03/24 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task |  | Service desk tower decommissioned an exit from Capgemini complete | 0 days | Fri 15/03/24 | Fri 15/03/24 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task |  | All applications transitioned | 0 days | Mon 02/09/24 | Mon 02/09/24 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task |  | All traffic cutover to target network | 0 days | Mon 02/09/24 | Mon 02/09/24 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
On Schedule |  | Dependencies |  |  |  | 0% |  |  |  | As Soon As Possible | Manually Scheduled |  | NA
On Schedule |  | Governance |  |  |  | 0% |  |  | Karen Anderson | As Soon As Possible | Manually Scheduled |  | NA
Late |  | TOM/ Common Services | 70 days | Fri 23/09/22 | Fri 30/12/22 | 0% |  |  |  | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | TOM including common services | 0 days | Fri 23/09/22 | Fri 23/09/22 | 100% |  | TOM | Mark Curry | As Soon As Possible | Manually Scheduled | what is the deliverable? | NA
Future Task | 2 | TOM (TBC) | 0 days | Fri 30/12/22 | Fri 30/12/22 | 0% |  | TOM | Mark Curry | As Soon As Possible | Manually Scheduled | what is the deliverable? | NA
Late |  | Hosting and Network | 695 days | Fri 29/04/22 | Fri 27/12/24 | 0% |  |  |  | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | Wi Fi vendor selected | 0 days | Fri 29/04/22 | Fri 29/04/22 | 100% |  | Hosting & Network | Carl Smith | As Soon As Possible | Auto Scheduled |  | NA
Complete | 3 | Supplier RFI reviewed and scored (down selection) | 0 days | Fri 13/05/22 | Fri 13/05/22 | 100% |  | Hosting & Network | Carl Smith | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | WiFi HW contract | 0 days | Fri 12/08/22 | Fri 12/08/22 | 100% |  | Hosting & Network | Carl Smith | As Soon As Possible | Auto Scheduled |  | NA
Complete | 3 | RFI responses from vendors | 0 days | Fri 26/08/22 | Fri 26/08/22 | 100% |  | Hosting & Network | Carl Smith | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | WiFi MS contracted | 0 days | Fri 16/09/22 | Fri 16/09/22 | 100% |  | Hosting & Network | Carl Smith | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | CTO Application Roadmap completed | 0 days | Thu 30/06/22 | Thu 30/06/22 | 100% |  | Hosting & Network | Carl Smith | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | Communication strategy for Capgemini | 0 days | Fri 01/07/22 | Fri 01/07/22 | 100% |  | Hosting & Network | Carl Smith | As Soon As Possible | Auto Scheduled |  | NA
Complete | 3 | Capgemini engaged in planning | 0 days | Fri 30/09/22 | Fri 30/09/22 | 100% |  | Hosting & Network | Carl Smith | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | Tom L1 complete | 0 days | Fri 30/09/22 | Fri 30/09/22 | 100% |  | Hosting & Network | Carl Smith | As Soon As Possible | Auto Scheduled |  | NA
Complete | 3 | Migration partner CMDS data | 0 days | Mon 03/10/22 | Mon 03/10/22 | 100% |  | Hosting & Network | Carl Smith | As Soon As Possible | Auto Scheduled |  | NA
Future Task | 3 | Ph1 Cloud landing zone design | 0 days | Fri 04/11/22 | Fri 04/11/22 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Non exotics app assessed | 0 days | Fri 18/11/22 | Fri 18/11/22 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Start WiFi implementation (AS) | 0 days | Wed 30/11/22 | Wed 30/11/22 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | AWS to Azure connectivity (temp) | 0 days | Wed 30/11/22 | Wed 30/11/22 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Ph1 landing zone ready | 0 days | Fri 09/12/22 | Fri 09/12/22 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | E2E hosting and network design | 0 days | Fri 23/12/22 | Fri 23/12/22 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | TOM interim | 0 days | Fri 30/12/22 | Fri 30/12/22 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Co Lo requirements defined | 0 days | Fri 06/01/23 | Fri 06/01/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Migration partner contract in place | 0 days | Fri 06/01/23 | Fri 06/01/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Ph2 cloud landing zone design | 0 days | Fri 13/01/23 | Fri 13/01/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Non Capgemini hosted app assessment | 0 days | Fri 20/01/23 | Fri 20/01/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Co Lo RFP issued | 0 days | Fri 20/01/23 | Fri 20/01/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Network RFP issued | 0 days | Fri 20/01/23 | Fri 20/01/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Confirm required shared service | 0 days | Fri 24/02/23 | Fri 24/02/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | TOM L2 | 0 days | Fri 10/03/23 | Fri 10/03/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Ph2 landing zone ready | 0 days | Fri 10/03/23 | Fri 10/03/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Co Lo supplier selected | 0 days | Fri 31/03/23 | Fri 31/03/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Networks Hub supplier selected | 0 days | Fri 31/03/23 | Fri 31/03/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | TOM in place with migration partner | 0 days | Fri 21/04/23 | Fri 21/04/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | 1st production app on tranistion to cloud | 0 days | Fri 28/04/23 | Fri 28/04/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | WiFi implemented (AS) | 0 days | Fri 19/05/23 | Fri 19/05/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Co Lo vendor contracted | 0 days | Fri 30/06/23 | Fri 30/06/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 1 | Network vendor contracted | 0 days | Fri 30/06/23 | Fri 30/06/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | AD handover | 0 days | Fri 17/11/23 | Fri 17/11/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Network ready | 0 days | Fri 24/11/23 | Fri 24/11/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Co Lo ready for migration | 0 days | Fri 24/11/23 | Fri 24/11/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Business app transformation final decision point | 0 days | Fri 29/12/23 | Fri 29/12/23 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 1 | WiFi implemented (0) | 0 days | Fri 01/03/24 | Fri 01/03/24 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 1 | All applications transitioned | 0 days | Mon 02/09/24 | Mon 02/09/24 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 1 | All traffic cutover to target network | 0 days | Mon 02/09/24 | Mon 02/09/24 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Capgemini data centres decommissioned for DLG | 0 days | Fri 27/12/24 | Fri 27/12/24 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Capgemini networks decommissioned for DLG | 0 days | Fri 27/12/24 | Fri 27/12/24 | 0% |  | Hosting & Network | Carl Smith | As Soon As Possible | Manually Scheduled |  | NA
Late |  | Service Desk | 430 days | Fri 22/07/22 | Fri 15/03/24 | 0% |  |  |  | As Soon As Possible | Auto Scheduled |  | NA
Complete | 3 | Shortlist the vendors for RFP | 0 days | Fri 22/07/22 | Fri 22/07/22 | 100% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Complete | 3 | Define Capgemini KT requirements | 0 days | Fri 12/08/22 | Fri 12/08/22 | 100% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | TOM 1 agreed (exec sourcing) | 0 days | Fri 30/09/22 | Fri 30/09/22 | 100% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Complete | 3 | Lessons learnt undertaken from previous Procurement | 0 days | Fri 30/09/22 | Fri 30/09/22 | 100% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Complete | 3 | Requirement defined for RFP | 0 days | Mon 03/10/22 | Mon 03/10/22 | 100% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | Service desk commercial strategy | 0 days | Mon 03/10/22 | Mon 03/10/22 | 100% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | RFP issued | 0 days | Fri 07/10/22 | Fri 07/10/22 | 100% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | Rebaselined plan based onTOM L1 | 0 days | Tue 11/10/22 | Tue 11/10/22 | 100% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | Rebaselined business case based on TOM L1 | 0 days | Tue 11/10/22 | Tue 11/10/22 | 100% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | RFP responses received | 0 days | Fri 18/11/22 | Fri 18/11/22 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | TOM L1 iterated (inc. Sourcing) | 0 days | Fri 13/01/23 | Fri 13/01/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Rebaselined plan based on sourcing model | 0 days | Fri 27/01/23 | Fri 27/01/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Rebaselined business case based on sourcing model | 0 days | Fri 27/01/23 | Fri 27/01/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Vendor selected | 0 days | Fri 17/02/23 | Fri 17/02/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 1 | Engage with Capgemini on exit | 0 days | Fri 14/04/23 | Fri 14/04/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Supplier contracted | 0 days | Fri 28/04/23 | Fri 28/04/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Capgemini exit date agreed | 0 days | Fri 19/05/23 | Fri 19/05/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Transition plan agreed | 0 days | Fri 16/06/23 | Fri 16/06/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Rebaselined plan based on contract agreement | 0 days | Fri 16/06/23 | Fri 16/06/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Rebaselined business case based on contract agreement | 0 days | Fri 16/06/23 | Fri 16/06/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | TOM L2 agreed (Service design and support model) | 0 days | Fri 30/06/23 | Fri 30/06/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Complete run cost model | 0 days | Fri 30/06/23 | Fri 30/06/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | OVT start | 0 days | Fri 01/09/23 | Fri 01/09/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Define the Service desk comms strategy | 0 days | Fri 29/09/23 | Fri 29/09/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | ITSM build and integration completed | 0 days | Fri 06/10/23 | Fri 06/10/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 1 | Service ready for transition | 0 days | Fri 27/10/23 | Fri 27/10/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Delivery comms completed | 0 days | Fri 17/11/23 | Fri 17/11/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | OVT completed | 0 days | Fri 17/11/23 | Fri 17/11/23 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Access revoked for legacy service desk | 0 days | Fri 23/02/24 | Fri 23/02/24 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 1 | Service desk tower decommissioned on exit from Capgemini completed | 0 days | Fri 15/03/24 | Fri 15/03/24 | 0% |  | Service Desk | Heidi Brearly | As Soon As Possible | Manually Scheduled |  | NA
Late |  | EUC | 400 days | Fri 19/08/22 | Fri 01/03/24 | 0% |  |  |  | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | App packaging service contract | 0 days | Fri 19/08/22 | Fri 19/08/22 | 100% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | Develop DLG AVD | 0 days | Fri 19/08/22 | Fri 19/08/22 | 100% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | SI completed | 0 days | Fri 19/08/22 | Fri 19/08/22 | 100% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | ServiceNow Go Live | 0 days | Fri 26/08/22 | Fri 26/08/22 | 100% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | App packaging service starts | 0 days | Fri 09/09/22 | Fri 09/09/22 | 100% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | Start app conversion | 0 days | Fri 30/09/22 | Fri 30/09/22 | 100% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | Start pilot for business areas | 0 days | Fri 07/10/22 | Fri 07/10/22 | 100% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | Start conversion of physical desktops | 0 days | Fri 07/10/22 | Fri 07/10/22 | 100% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Start EUDA discovery | 0 days | Fri 04/11/22 | Fri 04/11/22 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Model office fit out | 0 days | Wed 16/11/22 | Wed 16/11/22 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Start migration of BU to AVD | 0 days | Fri 25/11/22 | Fri 25/11/22 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Start data migration discovery | 0 days | Fri 02/12/22 | Fri 02/12/22 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Agree TOM for other service items | 0 days | Fri 06/01/23 | Fri 06/01/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Data analysis | 0 days | Fri 13/01/23 | Fri 13/01/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | EUDA analysis | 0 days | Fri 20/01/23 | Fri 20/01/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | High density wireless network services | 0 days | Fri 27/01/23 | Fri 27/01/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Agree data migration rules | 0 days | Fri 10/02/23 | Fri 10/02/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Agree EUDA approach | 0 days | Tue 28/02/23 | Tue 28/02/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Services contract TOM for other service items | 0 days | Fri 17/03/23 | Fri 17/03/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Finish desktop conversion | 0 days | Fri 31/03/23 | Fri 31/03/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Start deployment of services to in scope locations | 0 days | Fri 14/04/23 | Fri 14/04/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | End of business pilot DLG AVD | 0 days | Fri 28/04/23 | Fri 28/04/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Room booking service remdiation | 0 days | Fri 26/05/23 | Fri 26/05/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Wireless print service | 0 days | Fri 26/05/23 | Fri 26/05/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Local internet Telephony services | 0 days | Fri 26/05/23 | Fri 26/05/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Local thin client services | 0 days | Fri 26/05/23 | Fri 26/05/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Data migration complete | 0 days | Fri 25/08/23 | Fri 25/08/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | EUDA remediation complete | 0 days | Fri 22/09/23 | Fri 22/09/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | End of AVD migration | 0 days | Fri 13/10/23 | Fri 13/10/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | End of App conversion | 0 days | Fri 20/10/23 | Fri 20/10/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | O365 messaging complete | 0 days | Fri 24/11/23 | Fri 24/11/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Physical desktop replacement | 0 days | Fri 22/12/23 | Fri 22/12/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Office break fix service | 0 days | Fri 22/12/23 | Fri 22/12/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Audio visual support service | 0 days | Fri 22/12/23 | Fri 22/12/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Deskside support services | 0 days | Fri 22/12/23 | Fri 22/12/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Migration of AD to cloud | 0 days | Fri 22/12/23 | Fri 22/12/23 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 1 | File shares migrated | 0 days | Fri 01/03/24 | Fri 01/03/24 | 0% |  | EUC | Richard Higgins | As Soon As Possible | Manually Scheduled |  | NA
Late |  | Security Re-platforming | 385 days | Fri 20/05/22 | Fri 10/11/23 | 0% |  |  |  | As Soon As Possible | Auto Scheduled |  | NA
Complete | 3 | Capgemini WORs/WO | 0 days | Fri 20/05/22 | Fri 20/05/22 | 100% |  | Security | Paul Cochrane | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | LR forecast commercials approved | 0 days | Fri 20/05/22 | Fri 20/05/22 | 100% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | LR pilot commenced | 0 days | Mon 15/08/22 | Mon 15/08/22 | 100% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Complete | 3 | Capgemini WORs/WO | 0 days | Fri 02/09/22 | Fri 02/09/22 | 100% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | CA forecast commercials approved | 0 days | Fri 30/09/22 | Fri 30/09/22 | 100% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Complete | 2 | CA Pilot commenced | 0 days | Fri 21/10/22 | Fri 21/10/22 | 100% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | LogRhythm pilots complete | 0 days | Fri 04/11/22 | Fri 04/11/22 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Venafi forecast commercials approved | 0 days | Fri 18/11/22 | Fri 18/11/22 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | LogRhythm design and build complete | 0 days | Fri 02/12/22 | Fri 02/12/22 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Capgemini WORs/WO | 0 days | Fri 16/12/22 | Fri 16/12/22 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | CyberArk pilots complete | 0 days | Fri 06/01/23 | Fri 06/01/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | LogRhythm migration complete | 0 days | Fri 10/03/23 | Fri 10/03/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Venafi pilot complete | 0 days | Fri 17/03/23 | Fri 17/03/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | CyberArk design and build complete | 0 days | Fri 17/03/23 | Fri 17/03/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Venafi design and build complete | 0 days | Fri 31/03/23 | Fri 31/03/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | LogRhythm decommissioned from DC | 0 days | Fri 07/07/23 | Fri 07/07/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Forescout and Skybox solution decision point | 0 days | Fri 21/07/23 | Fri 21/07/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Venafi migration complete | 0 days | Fri 21/07/23 | Fri 21/07/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | CyberArk migration complete | 0 days | Fri 01/09/23 | Fri 01/09/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | CyberArk decommissioned from DC | 0 days | Fri 27/10/23 | Fri 27/10/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Venafi decommissioned from DC | 0 days | Fri 10/11/23 | Fri 10/11/23 | 0% |  | Security | Paul Cochrane | As Soon As Possible | Manually Scheduled |  | NA
Late |  | Security - Abient | 630 days | Fri 22/07/22 | Fri 20/12/24 | 0% |  |  |  | As Soon As Possible | Auto Scheduled |  | NA
Complete | 3 | Requirements gathering | 0 days | Fri 22/07/22 | Fri 22/07/22 | 100% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Complete | 3 | Dependency workshops | 0 days | Fri 22/07/22 | Fri 22/07/22 | 100% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Complete | 3 | E5 step up licences procured | 0 days | Fri 22/07/22 | Fri 22/07/22 | 100% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Complete | 3 | DLP design completed | 0 days | Fri 26/08/22 | Fri 26/08/22 | 100% |  | Security | Raj Raghav | As Soon As Possible | Auto Scheduled |  | NA
Complete | 3 | EPP & EDR design completed | 0 days | Fri 02/09/22 | Fri 02/09/22 | 100% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Late | 3 | Email hygiene design completed | 0 days | Fri 30/09/22 | Fri 30/09/22 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Late | 3 | Cloud app security design completed | 0 days | Tue 18/10/22 | Tue 18/10/22 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | DLP pilot completed | 0 days | Fri 25/11/22 | Fri 25/11/22 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Design phase completed | 0 days | Fri 23/12/22 | Fri 23/12/22 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Email hygiene completed | 0 days | Fri 03/02/23 | Fri 03/02/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Cloud app security pilot completed | 0 days | Fri 24/02/23 | Fri 24/02/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | DLP migrated | 0 days | Fri 03/03/23 | Fri 03/03/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | EDP & EDR pilot completed | 0 days | Fri 17/03/23 | Fri 17/03/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Cloud app security migrated | 0 days | Fri 19/05/23 | Fri 19/05/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Pilot phase completed | 0 days | Fri 30/06/23 | Fri 30/06/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Legacy email routing. Email hygiene & CASS entries removed | 0 days | Fri 18/08/23 | Fri 18/08/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | EPP & EDR migrated | 0 days | Fri 08/09/23 | Fri 08/09/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Legacy DLP & AIP decommissioned | 0 days | Fri 08/09/23 | Fri 08/09/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 3 | Legacy EPP & EDR decommissioned | 0 days | Fri 01/12/23 | Fri 01/12/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 1 | Migration of security tools completed | 0 days | Fri 22/12/23 | Fri 22/12/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Symantec estate decommissioned | 0 days | Fri 22/12/23 | Fri 22/12/23 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Project Abient completed/closed | 0 days | Fri 20/12/24 | Fri 20/12/24 | 0% |  | Security | Raj Raghav | As Soon As Possible | Manually Scheduled |  | NA
Late |  | Security - Rigel | 624 days | Mon 01/08/22 | Fri 20/12/24 | 0% |  |  |  | As Soon As Possible | Auto Scheduled |  | NA
Complete | 3 | Kick off initiated | 0 days | Mon 01/08/22 | Mon 01/08/22 | 100% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | As is state baselined | 0 days | Mon 03/10/22 | Mon 03/10/22 | 100% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Auto Scheduled |  | NA
Complete | 2 | RFI/RFP reqs agreed | 0 days | Fri 30/09/22 | Fri 30/09/22 | 100% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Auto Scheduled |  | NA
Late | 2 | Rigel RFP issued | 0 days | Mon 10/10/22 | Mon 10/10/22 | 0% |  | Security | Gerrad Olisa-Ashar | Start No Earlier Than | Auto Scheduled |  | NA
Future Task | 2 | Target state defined | 0 days | Fri 25/11/22 | Fri 25/11/22 | 0% |  | Security | Gerrad Olisa-Ashar | Start No Earlier Than | Auto Scheduled |  | NA
Future Task | 2 | Rigel vendor selected | 0 days | Fri 02/12/22 | Fri 02/12/22 | 0% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Internal capability commences | 0 days | Fri 30/12/22 | Fri 30/12/22 | 0% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Supplier contracted (TBC) | 0 days | Fri 24/02/23 | Fri 24/02/23 | 0% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | KT and Training commence | 0 days | Fri 31/03/23 | Fri 31/03/23 | 0% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | KT and training completed | 0 days | Fri 22/09/23 | Fri 22/09/23 | 0% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Internal capability built | 0 days | Fri 22/09/23 | Fri 22/09/23 | 0% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Dual running commences eg. SOC | 0 days | Fri 29/09/23 | Fri 29/09/23 | 0% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Manually Scheduled |  | NA
Future Task | 2 | Dual running completed eg. SOC | 0 days | Fri 20/12/24 | Fri 20/12/24 | 0% |  | Security | Gerrad Olisa-Ashar | As Soon As Possible | Manually Scheduled |  | NA
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use different icons to identify milestone levels, level 1 star, level 2 triangle, level 3 diamond Reply: Rag status aligned
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Milestone = Duration 0 days
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Conditional Format RAG Blue, Red, Amber(at Risk) , Green (In Progress/On Track) Reply: If 0, then green unless Finish date is less than today Reply: If it is overdue, then Red, less than today and % complete is not 100