## Project Plan
Stage | Stage ID | Stage Description | Task ID | Task Name | Notes | Owner | Estimated Start Date | Estimated End Date | Actual Start Date | Actual End Date | Milestone | % Completion
Discovery | 0 | Source System Candidates | 1 | Identify and gain read-only access to all the required source systems and databases, understand the source system data volume and complexity. | Rightio resource to provide a comprehensive list of all the source systems, including the purpose and data captured by each. | Rightio | 2023-09-15 | 2023-09-22 |  |  |  | 100%
Discovery | 1 | List of required data items | 2 | Document all the required data items to meet current and future business needs | Assuming existing reports has enough / correct information to use reducing reliance on Rightio BA resource | DF | 2023-09-15 | 2023-09-29 |  |  |  | 100%
Discovery | 2 | Data Dictionary | 3 | Prepare data dictionary to show data item lineage from source system | Assuming existing reports has enough / correct information to use reducing reliance on Rightio BA resource | DF | 2023-09-15 | 2023-09-29 |  |  |  | 100%
Discovery | 3 | Data Mapping | 4 | Create a data map to align similar data items , for example , status values, active, true, 1, live, should be mapped into a single value active. Mapping attributes to entities | Streamline similar data items values, confirm with the business before implementation | DF | 2023-09-15 | 2023-09-29 |  |  |  | 100%
Discovery | 4 | Business Rules / Logic | 5 | Define business rule and logic for measure calculations, logical data grouping, data categorisation etc | Assuming existing reports has enough / correct information to use reducing reliance on Rightio BA resource. Rightio to provide comprehensive list and sample reports, including budget/target/forecast data. | Rightio | 2023-09-22 | 2023-09-29 |  |  |  | 75%
Discovery | 5 | Security & Compliance | 6 | Determine security and compliance requirements - sensitvity labels, data compartmentalisation etc. | Rightio to provide details of security implementation, presumably data will only be visible within teams not between teams. Executive has overall visibility. | Rightio | 2023-09-15 | 2023-09-16 |  |  |  | 0%
Design / Data Modelling | 6 | Logical Model Design | 7 | Create a diagram of the logical data model showing all the entities, primary/foreign key relationships. Determine approach, star-schema or snow-flake or hybrid |  | DF | 2023-09-19 | 2023-09-22 |  |  |  | 25%
Database Development | 7 | Azure Admin Account | 8 | Set up Azure Admin Account | This assumes that the pre-requisite Azure Subscription has been provisioned, access to Rightio Azure portal will need to be granted. | WaveNet | 2023-09-15 | 2023-09-16 |  |  |  | 100%
Database Development | 8 | Azure Read-Only Account | 9 | Set up Azure Read-Only Account | This assumes that the pre-requisite Azure Subscription has been provisioned, access to Rightio Azure portal will need to be granted. | WaveNet | 2023-09-15 | 2023-09-16 |  |  |  | 100%
Database Development | 9 | Azure Configuration | 10 | Create Rightio resource group (if not already available), then create Rightio workspace using Azure configurator. | This assumes that the pre-requisite Azure Subscription has been provisioned, access to Rightio Azure portal will need to be granted. | WaveNet | 2023-09-15 | 2023-09-18 |  |  |  | 100%
Database Development | 10 | Logical Model Development | 11 | Converting the logical data model into the tables, views, columns, indexes, keys of the database |  | DF | 2023-09-23 | 2023-11-07 |  |  |  | 100%
Database Development | 11 | ETL Development | 12 | Create SSIS packages | The number of SSIS packages to create will depend on the number of tables in the source system database and the bare minimum required from the source systems. | DF | 2023-09-23 | 2023-11-07 |  |  | Y | 100%
Database Development | 12 | Database House-keeping | 13 | Create and configure Audit and Error Logging, source control. | Used to capture failure / success of process runs, useful for notification purposes, and change control. | DF | 2023-09-23 | 2023-09-24 |  |  |  | 100%
Testing | 13 | User Acceptance Testing | 14 | Business to test the figures from the Database | Rightio to compare database figures with existing reports to determine data integrity , robustness, confirm logical grouping , categorisation etc, this will be an excel dump based on existing reporting criteria, an assigned resource will be required. | Rightio | 2023-11-08 | 2023-11-15 |  |  | Y | 50%
Testing | 14 | User Acceptance Testing | 15 | Debugging / Issue Resolution | Debugging , application of fixes to issues raised above | DF | 2023-11-09 | 2023-11-16 |  |  |  | 0%
Release | 15 | Sign-off on Database Development | 16 | Sign-off on Database Development, agree / set schedule frequency for data loads | Provided UAT passes Rightio signs off on release | Rightio | 2023-11-17 | 2023-11-20 |  |  | Y | 0%
Reporting / Analytics Development | 16 | Tabular Modelling | 17 | Develop tabular model for Power BI reporting |  | DF | 2023-11-21 | 2023-12-05 |  |  |  | 100%
Reporting / Analytics Development | 17 | Power BI Dashboard Development | 18 | Develop Power BI reporting dashboards, paginated reports | Rightio to provide branding assets, logo etc, agree colour scheme for dashobard/reports. | DF | 2023-12-06 | 2023-12-15 |  |  | Y | 100%
Reporting / Analytics Development | 18 | Publish to Power BI Service | 19 | Published Dashboard/report to power BI Service, apply security, sensitivity labels and set refresh schedule frequency | This assumes that the Power BI license has been purchased, I have been made admin user and the environment has been configured properly. If Rightio agrees, I can configure the Power BI environment to the required specification. Azure Active Directory groups will need to be created to control access to the Power BI environment and to the data. | DF | 2023-12-15 | 2023-12-15 |  |  | Y | 100%
Reporting / Analytics Development | 19 | Product Demo | 20 | Demonstration of dashboard, how to use, take feedback for continuous improvement |  | Df | 2023-12-16 | 2023-12-19 |  |  |  | 75%
Formulas:
Estimated Start Date = [Estimated Start Date, row above]
Estimated Start Date = [Estimated End Date]-3
Estimated End Date = [Estimated Start Date]+7
Estimated End Date = Table1[[#This Row],[Estimated Start Date]]+14

## Project Schedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | RIGHTIO DATA PLATFORM
Enter Company Name in cell B2. | Company Name: |  | Rightio
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Project Lead |  | Damian Fadahunsi | Project Start: | 2023-09-15
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  |  | Display Week: | 1 |  |  | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [6 empty] | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06 | [6 empty] | 2023-11-13 | [6 empty] | 2023-11-20 | [6 empty] | 2023-11-27 | [6 empty] | 2023-12-04 | [6 empty] | 2023-12-11 | [6 empty] | 2023-12-18
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2023-09-11 to 2023-12-24
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK |  | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2023-09-11 to 2023-12-24
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Phase 1 - Discovery
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Source System Candidates | Identify and gain read-only access to all the required source systems and databases, understand the source system data volume and complexity. | Rightio | 100% | 2023-09-15 | 2023-09-22 | 8
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | List of required data items | Document all the required data items to meet current and future business needs | DF | 100% | 2023-09-15 | 2023-09-29 | 15
| Data Dictionary | Prepare data dictionary to show data item lineage from source system | DF | 100% | 2023-09-15 | 2023-09-29 | 15
| Data Mapping | Create a data map to align similar data items , for example , status values, active, true, 1, live, should be mapped into a single value active. Mapping attributes to entities | DF | 100% | 2023-09-15 | 2023-09-29 | 15
| Business Rules / Logic | Define business rule and logic for measure calculations, logical data grouping, data categorisation etc | Rightio | 75% | 2023-09-22 | 2023-09-29 | 8
| Security & Compliance | Determine security and compliance requirements - sensitvity labels, data compartmentalisation etc. | Rightio | 0% | 2023-09-15 | 2023-09-16
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Phase 2 - Design / Data Modelling
| Logical Model Design | Create a diagram of the logical data model showing all the entities, primary/foreign key relationships. Determine approach, star-schema or snow-flake or hybrid | DF | 25% | 2023-09-19 | 2023-09-22 | 4
Sample phase title block | Phase 3 - Database Development
| Azure Admin Account | Set up Azure Admin Account | WaveNet | 100% | 2023-09-15 | 2023-09-16 | 2
| Azure Read-Only Account | Set up Azure Read-Only Account | WaveNet | 100% | 2023-09-15 | 2023-09-16 | 2
| Azure Configuration | Create Rightio resource group (if not already available), then create Rightio workspace using Azure configurator. | WaveNet | 100% | 2023-09-15 | 2023-09-18 | 4
| Logical Model Development | Converting the logical data model into the tables, views, columns, indexes, keys of the database | DF | 100% | 2023-09-23 | 2023-11-07 | 46
| ETL Development | Create SSIS packages | DF | 100% | 2023-09-23 | 2023-11-07 | 46
| Database House-keeping | Create and configure Audit and Error Logging, source control. | DF | 100% | 2023-09-23 | 2023-09-24
Sample phase title block | Phase 4 - Testing
| User Acceptance Testing | Business to test the figures from the Database | Rightio | 50% | 2023-11-08 | 2023-11-15
| User Acceptance Testing | Debugging / Issue Resolution | DF | 0% | 2023-11-09 | 2023-11-16
Phase 5 - Release
| Sign-off on Database Development | Sign-off on Database Development, agree / set schedule frequency for data loads | Rightio | 0% | 2023-11-17 | 2023-11-20
Phase 6 - Reporting / Analytics Development
| Tabular Modelling | Develop tabular model for Power BI reporting | DF | 100% | 2023-11-21 | 2023-12-05
| Power BI Dashboard Development | Develop Power BI reporting dashboards, paginated reports | DF | 100% | 2023-12-06 | 2023-12-15
| Publish to Power BI Service | Published Dashboard/report to power BI Service, apply security, sensitivity labels and set refresh schedule frequency | DF | 100% | 2023-12-15 | 2023-12-15
| Product Demo | Demonstration of dashboard, how to use, take feedback for continuous improvement | Df | 75% | 2023-12-16 | 2023-12-19
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on F3: Damian: Project start delayed due to WaveNet resource availability